## Tasks
Task ID | Task | Category | Owner | Email | WhatsApp | Deadline | Status | Completed Date | Month | Year
ENG-001 | Replace worn conveyor belt on Packing Line 2 | Action Plan | Henry | giwamodupe@outlook.com | 2347064018988 | 2026-07-23 | Open |  | Jul | 2026
ENG-002 | Investigate recurring PLC communication fault | Action Plan | Okiki | okiki@company.com | 2348022222222 | 2026-07-28 | Open |  | Jul | 2026
ENG-003 | Raise purchase request for SKF bearings | Follow Up | Samson | samson@company.com | 2347089596097 | 2026-07-29 | Closed | 27/06/2026 | Jul | 2026
ENG-004 | Review preventive maintenance compliance | Follow Up | Efe | efe@company.com | 2348044444444 | 2026-07-31 | Closed | 27/06/2026 | Jul | 2026
ENG-005 | Replace faulty compressed air regulator | Action Plan | Henry | giwamodupe@outlook.com | 2347064018988 | 2026-07-27 | Open |  | Jul | 2026
ENG-006 | Inspect motor overload trips on Mixer 3 | Action Plan | Okiki | okiki@company.com | 2348022222222 | 2026-07-26 | Closed | 25/07/2026 | Jul | 2026
ENG-007 | Confirm delivery date for replacement gearbox | Follow Up | Samson | samson@company.com | 2347089596097 | 2026-07-30 | Open |  | Jul | 2026
ENG-008 | Conduct safety inspection after maintenance activities | Follow Up | Efe | efe@company.com | 2348044444444 | 2026-08-01 | Open |  | Aug | 2026
ENG-009 | Lubricate palletizer drive chain | Action Plan | Henry | giwamodupe@outlook.com | 2347064018988 | 2026-07-26 | Closed | 25/07/2026 | Jul | 2026
ENG-010 | Verify stock level of pneumatic cylinders | Follow Up | Samson | samson@company.com | 2347089596097 | 2026-08-02 | Open |  | Aug | 2026

## Summary Dashboard
ENGINEERING REVIEW BOARD DASHBOARD
CATEGORY BREAKDOWN
| Category | Total | Open | Closed | Overdue
| Follow Up | 5 | 3 | 2 | 0
| Action Plan | 5 | 3 | 2 | 2
OWNER PROGRESS
| Owner | Open | Closed | Progress
| Henry | 2 | 1
| Samson | 2 | 1
| Okiki | 1 | 1
| Efe | 1 | 1
OVERDUE WATCHLIST
| Task ID | Description | Category | Owner | Deadline
| ENG-001 | Replace worn conveyor belt on Packing Line 2 | Action Plan | Henry | 2026-07-23
| ENG-005 | Replace faulty compressed air regulator | Action Plan | Henry | 2026-07-27
Formulas:
Overdue = COUNTIFS(Tasks[Category], [Category], Tasks[Status], "Open", Tasks[Deadline], "<"&TODAY())
Category = IFERROR(__xludf.DUMMYFUNCTION("FILTER({Tasks[Task ID], Tasks[Task],Tasks[Category], Tasks[Owner],Tasks[Deadline]}, Tasks[Status]=""Open"", Tasks[Deadline]< TODAY())"),"ENG-001")
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.